## Issue-Log
ISSUE MANAGEMENT LOG
Project Name:
Project Manager Name:
Project Ref:
ID | Status | Priority | Issue Description | Owner | Estimated Resolution Date | Escalation Needed (Y/N)? | Impact | Actions | Date Identified | Logged By | Actual Resolution/Completion Date | Final Resolution & Follow-on actions
001 | Closed | Critical | Issues raised by board members about the O/S and security setup in the computers for loaning raised.. |  |  | Yes | Potential project cancellation or significant delay. | Meet with board members to review the security issues and how the O/S was set up following a locked down version of Windows 10. |  | John Doe |  | Board appraised the information and wexpressed satisfaction with the high levels of security. The board approved on 12/07.
002 | Closed | High | Work station 10 is giving occasional 'blue screen of death' due to system fault. | Jane D. |  | No | Unit has become unreliable and is causing data loss and disruption during work. | Reformat hard drive and reinstall software. Download backup files of data from hard disk. |  | Jane Doe | 2022-09-16 | Machine tests stable and all data accessible. Return to service.
003 | Work In Progress | Medium | Availability of replacement hard drives has dropped below required stock levels. | Fred D. |  | Yes | Computers will not be able to be repaired if there are hard drive failures. | Order nedd to be placed with endorsed vendors. |  | Fred Doe
004 | Open | Low | Desktop printer used in training needs to be re-installed in training laptop pool. | Marg P. |  | No | Training will be suspended if the job is not finished by end of month. | Schedule work for ealiest time this week. |  | Marg P.
|  |  | This template was provided by | https://www.stakeholdermap.com/
Note on A12: A unique ID number
Note on B12: Status: - Open: The issue is currently open but has not yet been addressed. - Work In Progress: The issue is being actively worked to develop a resolution. - Closed: The issue is no longer considered an active project threat and can be closed with or without resolution.
Note on C12: Critical, High, Medium, Low. Critical: Issue will stop project progress. High: Issue will likely impact budget, schedule or scope. Medium: Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope. Low: Issue is low impact and/or low effort to resolve.
Note on D12: Give a brief description of the issue.
Note on E12: The individual most responsible for working towards resolving the issue.
Note on F12: Estimated or target date for completion of actions.
Note on G12: “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on H12: Describe the impact of the issue. This may be in terms of the project constraints of time, cost and scope. See http://www.stakeholdermap.com/project-management/project-triangle.html
Note on I12: Actions to mitigate the issue, avoid the issue or resolve the issue.
Note on J12: The date that the issue was identified.
Note on L12: Actual completion date.
Note on M12: Document the final outcome. Is the issue resolved and if so how? Are there any follow-on actions? Are there any follow-on risks?

## severity-levels
Issue severity | Description
Critical | Issue will stop project progress.
High | Issue will likely impact budget, schedule or scope.
Medium | Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope.
Low | Issue is low impact and/or low effort to resolve.

## RESOURCES
Project Management resources
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
20 Common Project Risks
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel

## CUSTOMIZE
How to change or remove the cell colours in the Priority and 'Escalation needed?' column.
Conditional formatting is used to set the cell fill colour.
To change the fill colour. Click on Home > Conditional Formatting > Manage Rules…